## Sheet1
September ERP & POS development plan
| function | Type | Start date | End date | Check date | Status |  | function | Type | start date | end date | check date | status
1 | user permission validation | ERP | started | 2020-09-08 | 2020-09-08 |  | 1 | connect the credit and debit account | Accounting | 2020-09-10 | 2020-09-11 | 2020-09-12
2 | POS report validation | ERP | started | 2020-09-10 | 2020-09-10 |  | 2 | notification background task | Accounting | 2020-09-12 | 2020-09-12 | 2020-09-13
3 | Integreation between user permission and branch structure | ERP | 2020-09-10 | 2020-09-11 | 2020-09-12 |  | 3 | auto post background task | Accounting | 2020-09-17 | 2020-09-18 | 2020-09-18
4 | Stock calculation validation | ERP | 2020-09-10 | 2020-09-11 | 2020-09-12 |  | 4 | notification modal UI/UX | Accounting | 2020-09-19 | 2020-09-20 | 2020-09-20
5 | datetime synchronize between erp and pos | ERP & POS | 2020-09-10 | 2020-09-11 | 2020-09-12 |  | 5 | SMS integration testing | CRM | 2020-09-21 | 2020-09-23 | 2020-09-23
6 | Promo re-check on POS | POS | 2020-09-12 | 2020-09-12 | 2020-09-13 |  | 6 | Email integration testing | CRM | 2020-09-21 | 2020-09-23 | 2020-09-23
7 | a new table if there is no floor plan | POS | 2020-09-12 | 2020-09-12 | 2020-09-13 |  | 7 | Whatsapp bot | CRM | Oct.
8 | the database migration by the branch | ERP | 2020-09-13 | 2020-09-16 | 2020-09-16 |  | 8 | CRM report | CRM | Oct.
9 | Item transfer on POS | POS | 2020-09-17 | 2020-09-18 | 2020-09-18
10 | Main reading style modification on POS | POS | 2020-09-17 | 2020-09-18 | 2020-09-18
11 | Validation on Order Form | POS | 2020-09-17 | 2020-09-18 | 2020-09-18
12 | Table data empty display on POS | POS | 2020-09-17 | 2020-09-18 | 2020-09-18
13 | End of day to open table and delivery transition on POS | POS | 2020-09-19 | 2020-09-20 | 2020-09-20
14 | The added item print ability confirmation | POS | 2020-09-19 | 2020-09-20 | 2020-09-20
15 | Print format & data visibility & printer connection by IP | POS | 2020-09-19 | 2020-09-20 | 2020-09-20
16 | latest orders and upcoming reservations on POS Home's page | POS | 2020-09-19 | 2020-09-20 | 2020-09-20
17 | ERP maintenance | ERP | 2020-09-21 | 2020-09-23 | 2020-09-23
18 | POS maintenance | POS | 2020-09-24 | 2020-09-25 | 2020-09-25
19 | POS production version | POS | 2020-09-26 | 2020-09-27 | 2020-09-27
20 | Export the each modules as the production version | ERP | 2020-09-28 | 2020-09-30 | 2020-09-30